## Sheet1
Script Status
First iteration does not have to include validation. That will have to be done in next iteration though.
Scripts List | Output Pattern | Logging | Error Handling | Synopsis | Who | Estimate Done Date |  | Scripts List | Check Validation | Who | Estimate Done Date
ConfigureInitiate.ps1 | Done | Done | Done | Done | Sayan | 2015-12-15 |  | ConfigureInitiate.ps1 | Not Done | Tracy
configureWinRM.ps1 | Done | Done | Done | Done | Sayan | 2015-12-14 |  | configureWinRM.ps1 | Not Done | Tracy
createPushCenterAgentTask.ps1 | Done | Done | Done | Done | Sayan | 2015-12-15 |  | createPushCenterAgentTask.ps1 | Not Done | Tracy
createSharedFolders.ps1 - moved into template | Done | Done | Done | Done | Sayan | 2015-12-14 |  | createSharedFolders.ps1 | Not Done | Tracy
GetDTD.ps1 | Done | Done | Done | Done | Sayan | 2015-12-15 |  | GetDTD.ps1 | Not Done | Tracy
addHostnamesSingleIP.ps1 | Done | Done | Done | Done | Sayan | 2015-12-15 |  | addHostnamesSingleIP.ps1 | Not Done | Tracy
metascan.ps1 | Done | Done | Done | Done | Sayan | 2015-12-15 |  | metascan.ps1 | Not Done | Tracy
msdtcTest | Not Done | Not Done | Not Done | Not Done | Tracy | Later |  | msdtcTest | Not Done | Tracy
Msutil.ps1 | Moved into template |  |  |  | Tracy | 2015-12-15 |  | Msutil.ps1 | Not Done | Tracy
registerAppCert.ps1 | Done | Done | Done | Done | Sayan | 2015-12-14 |  | registerAppCert.ps1 | Not Done | Tracy
registerUrls.ps1 | Done | Done | Done | Done | Sayan | 2015-12-14 |  | registerUrls.ps1 | Not Done | Tracy
SetFolderPermissions.ps1 | Moved into template |  |  |  | Tracy | 2015-12-15 |  | SetFolderPermissions.ps1 | Not Done | Tracy
SetSslRenegotiationFlag.ps1 | Done | Done | Done | Done | Sayan | 2015-12-15 |  | SetSslRenegotiationFlag.ps1 | Not Done | Tracy
stats.ps1 | Moved into template |  |  |  | Tracy | 2015-12-15 |  | stats.ps1 | Not Done | Tracy
Initial running of the script on PRWEB34 to observe errors or unexpected behaviour.
Scripts List | Script has been run on PRWEB34 | Errors? | Error Status |  |  |  | Assigned
ConfigureInitiate.ps1 | Yes | Yes | See work log IXP-825 |  |  |  | ME
configureWinRM.ps1 | Yes | Yes | See work log IXP-819 |  |  |  | SB
createPushCenterAgentTask.ps1 | Yes | Yes | See work log IXP-820 |  |  |  | SB
createSharedFolders.ps1 | Template | Template | N/A |  |  |  | -
GetDTD.ps1 | Yes | Yes | See work log IXP-830 |  |  |  | TH
addHostnamesSingleIP.ps1 | Yes | No | N/A |  |  |  | -
metascan.ps1 | Yes | Yes | See work log IXP-823 |  |  |  | SB
msdtcTest | Later | [5 empty] | -
Msutil.ps1 | Template | Template | N/A |  |  |  | -
registerAppCert.ps1 | Yes | Yes | See work log IXP-821 |  |  |  | TH
registerUrls.ps1 | Yes | No | N/A |  |  |  | -
SetFolderPermissions.ps1 | Template | Template | N/A |  |  |  | -
SetSslRenegotiationFlag.ps1 | No | [5 empty] | SB
stats.ps1 | Template | Template | N/A |  |  |  | -