## Sequence
Proposed Virtual machine Phase 2 Web server buildout sequence.
Environment Tasks |  | Action | Who | Verification | Documentation
1 | Identify server name and assign static IP |  | DCS | ipconfig | Jira ticket
2 | Configure AD Framework and | Run script | DCS | Inspect AD | Jira ticket
3 | Create PAC secrets |  |  | Inspect PAC Secrets page. | Jira ticket
4 | BuildOutSetup.config | Add code version and machine |  | Visual inspection
5 | Update the Group Policy for the Windows Firewalls on the Production SQL Server databases |  | SEC | Visual inspection | Jira ticket
6 | Update description of Mongo IPTables firewall (Puppet) changes |  | SEC | Visual inspection | Jira ticket
7 | AppFabric Windows Firewall Group Policy Update |  | SEC | Visual inspection | Jira ticket
8 | Add the node in F5 - add to member iRule |  | DCS | Visual inspection | Jira ticket
9 | Create DTD for new server | Steps in Jira ticket | RM | Inspect latest DTD folder | Jira ticket
10 | Copy Latest DTD to SJMGDEP01 server | Run script | RM | Inspect E:\config folder | Jira ticket
11 | Add server to the auto deploy process | Steps in Jira ticket | RM | Inspect configuration files | Jira ticket
12 | AppFabric Cluster | Add the new server | DCS | AppFabric Test | SOP and Checklist
Phase 2 Template
1 | Create clone | Clone from template | DCS | N/A
2 | Add server to domain |  | DCS | Log onto server? | Jira ticket
3 | Servername certificate - SJPRWEBXX.rhf.ad | Verify existence. | DCS | MMC | Jira ticket
4 | Phase 2 clone verification | Run script | DCS | All tests pass | New
Phase 2 - Configure server for RelayHealth
1 | Buildout Scripts | Run new buildout script | DCS | Note: see Buildout Scripts List | SOP and Checklist
2 | Configure Initiate NIM LDAP - SJPRETL01 | Create users in Workbench application | DCS | Login as each user. | SOP and Checklist
3 | Think about putting a new test here |  |  |  | New
4 | Deploy code, Core, Interop, Hydroplatform, Verification | Auto deploy | DCS | WSC Test | SOP
5 | Monitor once the first service is started. |  | DCS/NOC
6 | Test | Run BVT
7 | Test | Run WSC Test | DCS | All tests pass | SOP and Checklist
8 | Enable in F5 | Monitor
9 | Hand off to NOC
Notes
1
2 | Verify log folder permissions | I have verified in PRWEB34 that the most common inetPub log folders exist.
3 | Verify msdtc configuration in the template
4

## Buildout Scripts List
| Main Buildout Files | Server Specific? | Has been run or included in General Template | Add to G Template | Run Post Template | Resulting Component
1 | C:\Buildout folders | No | No | Yes | N/A | Capability to run scripts
| runBuildoutScripts.ps1 | No | No | Yes | Yes | Capability to run scripts
2 | BuildoutScriptsFunctions.ps1 | No | No | Yes | Yes | Capability to run scripts
3 | buildoutSetup.config | No | No | Yes | Yes | Capability to run scripts
| Scripts List | Server Specific? | Has been run or included in General Template | Add to G Template | Run on new server clone? | Resulting Component | Script runs on PRWEB34 | Scripting Notes | Is script FINAL?
1 | AppFabricSetup.ps1 | No | Yes | No | No | AppFabric client | N/A | From hwebsource | Yes-Old
2 | audit.ps1 | No | Yes | No | No | User "everyone" and "E:\Resource folder", permissions - then remove "everyone" | N/A | From hwebsource | Yes-Old
3 | dotnetcharge.ps1 | No | Yes | No | No | C:\ProgramData\DotNetCharge | N/A | From hwebsource | Yes-Old
4 | unattended.cmd | No | Yes | No | No | Initiate MDE exe | N/A | From hwebsource | Yes-Old
5 | wintertree.ps1 | No | Yes | No | No | Wintertree application | N/A | From hwebsource | Yes-Old
6 | configureWinRM.ps1 | Yes | Yes | Remove | Yes | Creates listener | Yes | Remove winRM from template. See script running notes below. | No
7 | msdtcTest | Yes | No | No | Yes | Verifies firewalls are open and msdtc is setup correctly. | Not run yet | Needs DB instance, user and password | No
8 | addHostnamesSingleIP.ps1 | Yes | Yes | Remove | Yes | Has entries for the template machine: 10.100.105.40 - remove from template and inspect clone | Yes | Remove the old IP's from template hosts.txt file. Rename and add standard modifications. | No
9 | GetDTD.ps1 | Yes | No | No | Yes | environment.dtd file | Yes | See script testing notes below. | No
10 | registerUrls.ps1 | Yes |  |  | Yes |  | Yes |  | No
11 | registerAppCert.ps1 | Yes | No | No | Yes | HealthVault, EMR_Prod, VortexrToolsClient certificate registration. | Yes | Error: Access was not successfully obtained for the private key. | No
12 | metascan.ps1 | Yes | No | No | Yes | DCOM permissions | Yes | See script testing notes below. | No
13 | createPushCenterAgentTask.ps1 | Yes | No | No | Yes | PushCenterAgent task. | Yes | See script testing notes below. | No
14 | ConfigureInitiate.ps1 | Yes | No | No | Yes |  | Yes | See script testing notes below. | No
15 | SetSslRenegotiationFlag.ps1 | Yes | No | No | Yes | Specific to the IP | Not run yet |  | No
16 | stats.ps1 | No | No | Yes | No | Copies Stats Folder and FacsysDll files to C:\Windows\SYSWOW64. Also Runs Regsvr32 fxmsg32.dll - Add to template and inspect the clone. | Not run yet |  | No
19 | metascanInstall.bat | No | No | Yes | No | License | Not run yet |  | Yes
20 | createSharedFolders.ps1 | No | No | Yes | No | Add to template and inspect the clone. | Yes |  | No
| Msutil.ps1 | No | No | Yes | No | Add to template and inspect the clone. | Yes | See script testing notes below. | No
| SetFolderPermissions.ps1 | No | No | Yes | No | Users and folders in AccessPermissions.config. - Verify folders exist in the template and then run script. | Yes | Task: Compare folders in config file with what is on the server. See script testing notes below. | No
21 | Reinstall certificates | No | Yes | Yes |  | Need to be reinstalled. | Manual task |  | N/A
22 | Update Riverbed agent | No | Yes | Yes |  | Needs to be updated to latest version. | Nick Johnson |  | N/A
Script Testing Notes
| configureWinRM.ps1 | (1) Not able to get the -remove option to execute. (2) When creating a new listener, not getting the correct $service name. Getting "System.ServiceProcess.ServiceController". (3) Not displaying listener list in log, displays on host. (4) Using "winrm invoke Restore winrm/config" to remove listener for testing.
| GetDTD.ps1 | (1) Missing "}" at line 66 - fixed. (2) Cannot find source file… we don't have a MachineSpecifics folder for Web34. (3) Copied an existing folder for testing. (4) Commented out all functionality except for a source path test. Still getting "Cannot find path '\\Sjmgdep01\f$\SCM\Buildout\MachineSpecifics\' because it does not exist." message.
| registerAppCert.ps1 | Error: Access was not successfully obtained for the private key. At F:\SCM\Buildout\NewBuildout\BuildoutScriptsFunctions.ps1:139 char:3 - Invoke-Command -session $session -filePath $filePath -argumentList $argsList
| registerUrls.ps1 | Need to investigate what to add for validation.
| createPushCenterAgentTask.ps1 | (1) Fixed the previous missing ")" issues. (2) New issue: Cannot find Scheduled Task configuration file PushCenterAgent.xml - fixed by changing path in script to local root. (3) New issue: Running command: schtasks /Create /XML ./PushCenterAgent.xml /TN /RU "RHF.AD\SJPRWEB34TASK" /RP "xxxxx" /F schtasks : ERROR: Invalid syntax. Value expected for '/TN'. At line:1 char:9 + schtasks <<<< /Create /XML ./PushCenterAgent.xml /TN /RU "RHF.AD\SJPRWEB34TASK" /RP "Cn9.5-fB+D2p3*" /F 2>&1 + CategoryInfo : NotSpecified: (ERROR: Invalid ...cted for '/TN'.:String) [], RemoteException + FullyQualifiedErrorId : NativeCommandError Type "SCHTASKS /CREATE /?" for usage. Mon, 14 Dec 2015 13:41:36 GMT - Failed to create scheduled task PushCenterAgent
| SetFolderPermissions.ps1 | Cannot find path 'C:\Users\thartzler\Documents\Environmentdomain.config' because it does not exist. Need to figure out why it is looking in \thartzler folder. Added file to NewBuildout folder but that didn't make a difference. - Possible fix, this script is using $config instead of $EnvironmentConfig. Rename to $EnvironmentConfig.
| metascan.ps1 | Error: Exception calling ".ctor" with "1" argument(s): "String cannot be of zero length. Parameter name: name"
| Msutil.ps1 | Config File Corrupted Cannot find path 'C:\Users\thartzler\Documents\Environmentdomain.config' because it does not exist. Stopping the remote session Cannot find path 'C:\Users\thartzler\Documents\Environmentdomain.config' because it does not exist. At F:\SCM\Buildout\NewBuildout\BuildoutScriptsFunctions.ps1:139 char:3 + Invoke-Command -session $session -filePath $filePath -argumentList $argsList - Possible fix, this script is using $config instead of $EnvironmentConfig. Rename to $EnvironmentConfig.
| ConfigureInitiate.ps1 | Add the Initiate executable path to the Windows environment Path variable Add the Initiate Engine executable path to the Windows environment Path variable Environment-specific settings file 'Env.set.bat' does not exist at location E:\mpi\project\initiate\scripts\env.set.bat

## Phase2 Generic Template
Components added after the Phase 1 template.
Phase 2 Template (General)
| Agent | EVO AV
| Agent | Riverbed AppInternals
| Agent | SCOM
| Certificate Authorities | Multiple
| Certificates | Multiple
| Configuration | Machine Key, generic DTD
| Configuration | MSDTC
| Folder | C:\hwebsource …\
| Folder | C:\inetpub\logs\Logfiles …\
| Folder | C:\Setup\Metascan 3.9.2
| Folder | C:\temp folder
| Folder | E:\Config
| Folder | E:\HydroPlatform …\
| Folder | E:\InteropApplications …\
| Folder | E:\RelayHealth …\
| Folder | E:\RelayHealth\PatientEducation …\
| Folder | E:\RelayHealth\Resource …\
| Folder | E:\Verification …\
| Installed | AppFabric client
| Installed | Initiate MDE exe
| Installed | SMTP
| Installed | Third party applications
| Script | PushCenterAgent.ps1
| Updates | Windows patches

## Old vs New Scripts
OLD SCRIPTS | [6 empty] | New Buildout Scripts List
1 | BuildoutPackageExecuter.ps1 | [5 empty] | runBuildoutScripts.ps1
2 |  | BuildoutPackageExecuterFunctions.ps1 |  |  |  |  | BuildoutScriptsFunctions.ps1
3 |  | buildoutSetup.config |  |  |  |  | buildoutSetup.config
4 |  | Flashdeploy.ps1 |  |  |  |  | N/A
5 |  |  | install_blackbox.bat |  |  |  | N/A
6 |  | scriptbooter.ps1 |  |  |  |  | N/A
7 |  |  | ScriptBooterFunctions.ps1 |  |  |  | N/A
8 |  |  | hostnamessingleip.ps1 |  |  |  | hostnamessingleip.ps1
9 |  |  | dotnetcharge.ps1 |  |  |  | dotnetcharge.ps1
10 |  |  | stats.ps1 |  |  |  | stats.ps1
11 |  |  | newserver.ps1 |  |  |  | Copies Patient Education - N/A
12 |  |  |  | permtest.ps1 |  |  | registerUrls.ps1
13 |  |  |  | metascan.ps1 |  |  | metascan.ps1
14 |  |  | newserver2.ps1 |  |  |  | N/A
15 |  |  |  | audit.ps1 |  |  | audit.ps1
16 |  |  |  | wintertree.ps1 |  |  | wintertree.ps1
17 |  |  |  | hiddenshares.ps1 |  |  | createSharedFolders.ps1
18 |  |  | deploy.ps1 |  |  |  | ???
19 |  |  |  | deploy.ps1 |  |  | Auto Deploy
20 |  |  |  |  | Stop-Services.ps1 |  | Auto Deploy
21 |  |  |  |  | Get-HydroPlatformServicesConfigurations.ps1 |  | Auto Deploy
22 |  |  |  |  | Get-RelayServicesConfigurations.ps1 |  | Auto Deploy
23 |  |  |  |  | Get-InteropServicesConfigurations.ps1 |  | Auto Deploy
24 |  |  |  |  | Get-InitiateServicesConfigurations.ps1 |  | Auto Deploy
25 |  |  |  |  | unzip.version.ps1 |  | Auto Deploy
26 |  |  |  |  | Configure-EventSources.ps1 |  | Auto Deploy
27 |  |  |  |  | Configure-EventLogs.ps1 |  | Auto Deploy
28 |  |  |  |  | InteropApplications.deployversion.ps1 |  | Auto Deploy
29 |  |  |  |  | core.deployversion.ps1 |  | Auto Deploy
30 |  |  |  |  | CreateFolders.ps1 |  | Auto Deploy
31 |  |  |  |  | Get-RelayIISConfigurations.ps1 |  | Auto Deploy
32 |  |  |  |  | ConfigTestWeb.ps1 |  | Auto Deploy
33 |  |  |  |  | DeployWindowsServerAppFabric.ps1 |  | Auto Deploy
34 |  |  |  |  | Configure-Services.ps1 |  | Auto Deploy
35 |  |  |  |  | CreateScheduledTasks.ps1 |  | Auto Deploy
36 |  |  |  |  | logging.ps1 |  | Auto Deploy
37 |  |  |  |  | machinekey.ps1 |  | Auto Deploy
38 |  |  |  |  | Start-Services.ps1 |  | Auto Deploy
39 |  |  | Msutil.ps1 |  |  |  | Msutil.ps1
40 |  |  | SetFolderPermissions.ps1 |  |  |  | SetFolderPermissions.ps1
41 |  |  | Initiate.ps1 |  |  |  | ConfigureInitiate.ps1
42 |  |  |  | unattended.cmd |  |  | ConfigureInitiate.ps1
43 |  |  |  | initiatesetup.ps1 |  |  | ConfigureInitiate.ps1
44 |  |  |  |  | unattended.cmd |  | ConfigureInitiate.ps1
45 |  |  |  |  | createinitiate.bat |  | ConfigureInitiate.ps1
46 | [5 empty] | env.set.bat | ConfigureInitiate.ps1
47 | [5 empty] | GenerateConfig.bat | ConfigureInitiate.ps1
48 | [5 empty] | file.copy.bat | ConfigureInitiate.ps1
49 |  |  |  |  | droppingdatasource.bat |  | ConfigureInitiate.ps1
50 | [5 empty] | env.set.bat | ConfigureInitiate.ps1
51 | [5 empty] | datasource.drop.bat | ConfigureInitiate.ps1
52 |  |  |  |  | stoppinginstance.bat |  | ConfigureInitiate.ps1
53 | [5 empty] | env.set.bat | ConfigureInitiate.ps1
54 | [5 empty] | instance.stop.bat | ConfigureInitiate.ps1
55 |  |  |  |  | droppinginstance.bat |  | ConfigureInitiate.ps1
56 | [5 empty] | env.set.bat | ConfigureInitiate.ps1
57 | [5 empty] | instance.drop.bat | ConfigureInitiate.ps1
58 |  |  |  |  | creatingdatasource.bat |  | ConfigureInitiate.ps1
59 | [5 empty] | env.set.bat | ConfigureInitiate.ps1
60 | [5 empty] | datasource.create.bat | ConfigureInitiate.ps1
61 |  |  |  |  | creatinginstance.bat |  | ConfigureInitiate.ps1
62 | [5 empty] | env.set.bat | ConfigureInitiate.ps1
63 | [5 empty] | instance.create.bat | ConfigureInitiate.ps1
64 |  |  |  | installpassive.bat |  |  | ConfigureInitiate.ps1
65 |  |  | AppFabricSetup.ps1 |  |  |  | ???
66 |  |  |  |  | AppFabric.bat |  | ???
67 |  |  | hv.ps1 |  |  |  | registerAppCert.ps1
configureWinRM.ps1
GetDTD.ps1
PushCenterAgent.xml
SetSslRenegotiationFlag.ps1
Notes
Flashdeploy.ps1 |  |  |  | I think this included using dropbox to copy C:\hwebsource folders to the new server. How are we going to update new servers with updated source files?
install_blackbox.bat |  |  |  | Now that Riverbed is installed by GPO, I don't think we need this. Nick took a quick look at this file and doesn't think it applies anymore.
scriptbooter.ps1 |  |  |  | Investigate remaining code that would need to be run other than the scripts being called. If all the scripts are being called in the new buildout list, then this can be deprecated.
ScriptBooterFunctions.ps1 |  |  |  | Need to review the new scripts to see if they need any of these functions.
newserver.ps1 |  |  |  | Investigate remaining code that would need to be run other than the scripts being called.
newserver2.ps1 |  |  |  | Investigate remaining code that would need to be run other than the scripts being called.
AppFabricSetup.ps1 |  |  |  | Was commented out in deploy.ps1 - if all this did was to create the client, that is already in the template.
deploy.ps1 |  |  |  | This was the "deploy" script on DEP01 calling the "deploy" script on the server. Investigate remaining code to see what would need to be run other than "deploy.ps1".