## Sheet1
Script Status
First iteration does not have to include validation. That will have to be done in next iteration though.
Scripts List | Output Pattern | Logging | Error Handling | Synopsis | Who | Estimate Done Date | Scripts List | Check Validation | Who | Estimate Done Date
ConfigureInitiate.ps1 | Done | Done | Done | Done | Sayan | 2015-12-15 | ConfigureInitiate.ps1 | Not Done | Tracy
configureWinRM.ps1 | Done | Done | Done | Done | Sayan | 2015-12-14 | configureWinRM.ps1 | Not Done | Tracy
createPushCenterAgentTask.ps1 | Done | Done | Done | Done | Sayan | 2015-12-15 | createPushCenterAgentTask.ps1 | Not Done | Tracy
createSharedFolders.ps1 | Done | Done | Done | Done | Sayan | 2015-12-14 | createSharedFolders.ps1 | Not Done | Tracy
GetDTD.ps1 | Done | Done | Done | Done | Sayan | 2015-12-15 | GetDTD.ps1 | Not Done | Tracy
addHostnamesSingleIP.ps1 | Done | Done | Done | Done | Sayan | 2015-12-15 | addHostnamesSingleIP.ps1 | Not Done | Tracy
metascan.ps1 | Not Done | Not Done | Not Done | Not Done | Sayan | 2015-12-15 | metascan.ps1 | Not Done | Tracy
msdtcTest | Not Done | Not Done | Not Done | Not Done | Tracy | 2015-12-15 | msdtcTest | Not Done | Tracy
Msutil.ps1 | Not Done | Not Done | Not Done | Not Done | Sayan | 2015-12-15 | Msutil.ps1 | Not Done | Tracy
registerAppCert.ps1 | Done | Done | Done | Done | Sayan | 2015-12-14 | registerAppCert.ps1 | Not Done | Tracy
registerUrls.ps1 | Done | Done | Done | Done | Sayan | 2015-12-14 | registerUrls.ps1 | Not Done | Tracy
SetFolderPermissions.ps1 | Not Done | Not Done | Not Done | Not Done | Sayan | 2015-12-15 | SetFolderPermissions.ps1 | Not Done | Tracy
SetSslRenegotiationFlag.ps1 | Done | Done | Done | Done | Sayan | 2015-12-15 | SetSslRenegotiationFlag.ps1 | Not Done | Tracy
stats.ps1 | Not Done | Not Done | Not Done | Not Done | Sayan | 2015-12-15 | stats.ps1 | Not Done | Tracy
Initial running of the script on PRWEB34 to observe errors or unexpected behaviour.
Scripts List | Script has been run on PRWEB34 | Errors? | Error Status
ConfigureInitiate.ps1 | Yes | Yes | See work log IXP-825
configureWinRM.ps1 | Yes | Yes | See work log IXP-819
createPushCenterAgentTask.ps1 | Yes | Yes | See work log IXP-820
createSharedFolders.ps1 | Yes | No | N/A
GetDTD.ps1 | Yes | Yes | See work log IXP-830
addHostnamesSingleIP.ps1 | Yes | No | N/A
metascan.ps1 | Yes | Yes | See work log IXP-823
msdtcTest | No
Msutil.ps1 | Yes | Yes | No ticket - same type of issue as IXP-1266
registerAppCert.ps1 | Yes | Yes | See work log IXP-821
registerUrls.ps1 | Yes | No | N/A
SetFolderPermissions.ps1 | Yes | Yes | See work log IXP-1266
SetSslRenegotiationFlag.ps1 | No
stats.ps1 | No